## BLANK - Weekly Project Timeline
CS 422 PROJECT: Duck Planner
Ethan Dinh, Annika Huston, Nathan Gong |  |  |  |  | 2023-09-25 | 2023-10-02 |  | 2023-10-09 |  | 2023-10-16 |  | 2023-10-16 |  | 2023-10-23 |  | 2023-10-30
TASK NAME | ASSIGNED TO | START | END | STATUS | W | M | W | M | W | M | W | M | W | M | W | M | W | STATUS
Project Logistics | [17 empty] | Not Started
Finalize Project Idea + Flush out details | Team | 2023-09-27 | 2023-09-27 | Complete | [13 empty] | In Progress
Initialize Git Repository | Ethan | 2023-09-27 | 2023-09-27 | Complete | [13 empty] | Complete
Initialize Group Chat - iMessage | Team | 2023-09-27 | 2023-09-27 | Complete | [13 empty] | On Hold
Begin Writing SDS + SRS | Team | 2023-09-27 | 2023-10-16 | In Progress
Draft Project Proposal Presentation | Team | 2023-07-27 | 2023-10-09 | In Progress
Backend Development - WebScraping & Scheduling
Discuss frontend / backend interactions | Team |  |  | Complete
Use Selenium to see if the UO page can be scraped | Ethan |  |  | Complete
Create a python web scraper using selenium | Ethan |  |  | Complete
Link the CSV output from the scraper to a database | Ethan |  |  | Complete
Read in the CSV and store classes in an ADT | Ethan |  |  | Complete
Draft a backend TUI scheduler | Ethan |  |  | Complete