## BLANK - Weekly Project Timeline
CS 422 PROJECT: Duck Planner
Ethan Dinh, Annika Huston, Nathan Gong |  |  |  |  | 2023-09-25 | 2023-10-02 |  | 2023-10-09 |  | 2023-10-16 |  | 2023-10-23 |  | 2023-10-30 |  | 2023-11-06 |  | 2023-11-13 |  | 2023-11-20 |  | 2023-11-27 |  | STATUS
TASK NAME | ASSIGNED TO | START | END | STATUS | W | M | W | M | W | M | W | M | W | M | W | M | W | M | W | M | W | M | W | Not Started
Project Logistics |  |  |  |  | Project Logistics | [18 empty] | In Progress
Finalize Project Idea + Flush out details | Team | 2023-09-27 | 2023-10-02 | Complete | [19 empty] | Complete
Initialize Git Repository | Ethan | 2023-09-27 | 2023-10-02 | Complete | [19 empty] | On Hold
Initialize Group Chat - iMessage | Team | 2023-09-27 | 1900-01-09 04:48 | Complete
Writing SDS + SRS | Team | 2023-09-27 | 2023-11-29 | Complete
Draft Project Proposal Presentation | Team | 2023-09-27 | 2023-10-11 | Complete
Final Presentation | Team | 2023-11-22 | 2023-11-27 | Complete
Backend Development - WebScraping & Scheduling |  |  |  |  | Backend Development - WebScraping & Scheduling
Discuss frontend / backend interactions | Team | 2023-09-27 | 2023-10-02 | Complete
Use Selenium to see if the UO page can be scraped | Ethan | 2023-09-27 | 2023-10-02 | Complete
Create a python web scraper using selenium | Ethan | 2023-09-27 | 2023-10-02 | Complete
Link the CSV output from the scraper to a database | Ethan | 2023-10-16 | 2023-11-01 | Complete
Read in the CSV and store classes in an ADT | Ethan | 2023-09-27 | 2023-10-02 | Complete
Draft a backend TUI scheduler | Ethan | 2023-09-27 | 2023-10-02 | Complete
Implement Filters | Ethan | 2023-10-09 | 2023-11-15 | Complete
Backend Development - Database |  |  |  |  | Backend Development - Database
Initialize Database | Annika | 2023-09-27 | 2023-10-18 | Complete
Plan Architechture | Annika | 2023-10-02 | 2023-10-23 | Complete
Implement translation layer between scraper | Annika | 2023-10-05 | 2023-10-25 | Complete
Implement translation layer between frontend | Annika | 2023-10-16 | 2023-11-06 | Complete
Frontend Development |  |  |  |  | Frontend Development
Main HTML Framework | Nathan | 2023-10-09 | 2023-10-23 | Complete
Matrix View | Ethan | 2023-10-16 | 2023-11-08 | Complete
Inialize AWS Services | Ethan / Nathan | 2023-10-04 | 2023-11-22 | Complete
Map View | Ethan | 2023-11-06 | 2023-11-20 | Complete
Sorting Algorithms | Ethan | 2023-11-15 | 2023-11-22 | Complete
Login Page | Nathan | 2023-11-08 | 2023-11-22 | Complete
Host the Website | Ethan | 2023-10-25 | 2023-11-08 | Complete
Preview View | Nathan | 2023-10-11 | 2023-10-25 | Complete
Class Selection | Nathan | 2023-10-09 | 2023-10-23 | Complete